## Tutor Modeling Plan
| Workshop Start Date: | 2021-06-29 | Grade(s): | Content: | District:
Workbook Reference | Workshop | Deadline | Status | Element | Decision point | Decison Maker | Decision | Notes
1 | Program Aim | 2021-07-03 |  | Other | What are the most important design principles for us to consider?
2 | Program Aim | 2021-06-29 |  | Program Focus | What are the challenges we seek to address via our Value Proposition?
3 | Program Aim | 2021-07-03 |  | Program Focus | What are the needs and impact our high-impact tutoring initiative will address?
4 | Program Aim | 2021-07-03 |  | Program Focus | How are you targeting your tutoring, and what is your articulation for why tutoring is needed?
5 | Program Aim | 2021-07-03 |  | Other | What key resources, beyond money, will I leverage?
6 | Program Aim | 2021-07-03 |  | Other | What is my bottom line budget for tutoring?
7 | Program Aim | 2021-07-03 |  | Other | When are high-impact tutoring funds disbursed?
8 | Program Aim | 2021-07-03 |  | Other | Who will oversee the general initiative: strategy, hiring, tutors, instruction, and logistics?
9 | Program Aim | 2021-07-24 |  | Other | Who all is involved and what are their roles and responsibilities ?
10 | Program Aim | 2021-07-03 |  | Program Focus | What content areas will your tutoring program address?
11 | Program Aim | 2021-07-03 |  | Program Focus | What grade(s) will your tutoring program address?
12 | Program Aim | 2021-07-03 |  | Instruction | How often will tutoring sessions happen (days/week)?
13 | Program Aim | 2021-07-03 |  | Instruction | What will be the length of each ssession?
14 | Program Aim | 2021-07-03 |  | Learning Integration | What is the length of the tutoring program run (# of weeks)?
15 | Program Aim | 2021-07-03 |  | Instruction | How long will tutoring be offered (weeks/school year)?
16 | Program Aim | 2021-07-03 |  | Instruction | How will students and tutors collaborate (delivery mode)?
17 | Program Aim | 2021-07-10 |  | Learning Integration | When will tutoring sessions happen (time of day)?
18 | Program Aim | 2021-07-03 |  | Learning Integration | Where will tutoring sessions happen?
19 | Program Aim | 2021-07-03 |  | Program Focus | When will tutoring start?
20 | Program Aim | 2021-07-10 |  | Learning Integration | Will tutoring be voluntary or required?
21 | Identifying Students & Budget Needs | 2021-07-10 |  | Program Focus | What selection criteria will be used to for students?
22 | Identifying Students & Budget Needs | 2021-07-10 |  | Program Focus | How many total students will receive tutoring?
23 | Identifying Students & Budget Needs | 2021-07-10 |  | Instruction | What is the ratio of students to tutor per group?
24 | Identifying Students & Budget Needs | 2021-07-10 |  | Cohesion | What schools will take part in the tutoring program?
25 | Identifying Students & Budget Needs | 2021-07-10 |  | Tutor | How many total tutors are needed?
26 | Identifying Students & Budget Needs | 2021-07-10 |  | Tutor | Who is my ideal tutor?
27 | Identifying Students & Budget Needs | 2021-07-10 |  | Tutor | What tutor type will be utilizied?
28 | Identifying Students & Budget Needs | 2021-07-10 |  | Tutor | What is the tutor cost in the budget?
29 | Hiring & Training Tutors & Materials | 2021-07-17 |  | Instruction | What curriculum will be used?
30 | Hiring & Training Tutors & Materials | 2021-07-24 |  | Data Use | What progress monitoring tool(s) will be used?
31 | Hiring & Training Tutors & Materials | 2021-07-17 |  | Tutor | What days will tutoring occur?
32 | Hiring & Training Tutors & Materials | 2021-07-17 |  | Tutor | <if applicable> What tutoring providers will be used?
33 | Hiring & Training Tutors & Materials | 2021-07-24 |  | Tutor | What materials are needed for tutor recruitment and hiring?
34 | Hiring & Training Tutors & Materials | 2021-07-24 |  | Tutor | What is the interview process for tutors?
35 | Hiring & Training Tutors & Materials | 2021-07-17 |  | Tutor | When will initial tutoring training occur?
36 | Hiring & Training Tutors & Materials | 2021-07-24 |  | Tutor | What will be the content of initial tutor training?
37 | Evaluation & Communication | 2021-07-24 |  | Data Use | What is the progress monitoring cadence?
38 | Evaluation & Communication | 2021-07-24 |  | Data Use | What metrics will be used to monitor progress for both students and tutors?
39 | Evaluation & Communication | 2021-07-24 |  | Data Use | How and when will identified metrics be measured?
40 | Evaluation & Communication | 2021-07-24 |  | Learning Integration | What topics will be schools receive training on?
41 | Evaluation & Communication | 2021-07-24 |  | Learning Integration | What topics will teachers receive training on?
42 | Evaluation & Communication | 2021-07-24 |  | Learning Integration | What topics will caregivers receive training on?
43 | Evaluation & Communication | 2021-07-24 |  | Learning Integration | When will school and caregiver trainings take place?
44 | Evaluation & Communication | 2021-07-24 |  | Learning Integration | How will school and caregiver trainings be delivered (in-person, recorded webinars, Zoom meeting, etc)?
Note on A1: which of the purple is crucial to decide this week in order to move on vs. have an idea can i forecast this up front for all sessions before start designing deck -Stephanie Parkinson wkshop 1: data to make decisions, grades, content. DOR (stakeholder committee) -Stephanie Parkinson also what are giving a nod to vs. deciding -Stephanie Parkinson remember: tea is providing ACCESS to material (the decision is whether TEA material or your materials) -Stephanie Parkinson ---- do we need to link where this info is in the deck too -Stephanie Parkinson what is the final output/product? Here are all your notes and where you are doing? And then final - then you type in the playbook (planning guide and then a final playbook). -Stephanie Parkinson

## Budget Modeling
Estimated Bottom Line Budget: |  | Estimated Totals: | #DIV/0! | 0 | #DIV/0!
Percent of budget allocated: | 100% | Estimated Cost/Student: | #DIV/0! |  | #DIV/0!
Percentage of budget |  | Budget | Budget Items |  | Cost
Typical budget allotment | LEA amount
Tutor Costs
Suggested 70% Tutor costs will likely be the biggest expense. For most programs, personnel related costs account for 50-90% of the overall budget (inclusive of support personnel). Who you recruit for tutors drastically impacts this price point, along with the frequency and schedule of the program. To see estimated costs based on type of tutor, check out the workbook. Questions to consider: Are local wages below or above the national average provided? How will supply and demand affect the wage offered? | 70% | 0 | Tutor Wage (Prep Time/Training)
Tutor Wage (wtih Students)
Tutor Salary (if NOT paid hourly wage)
Number of students served
Student:Tutor Ratio (enter # of Ss per group)
How Many Groups Per Tutor
Duration of each tutor session (enter in hours)
How Many Times Does Each Group Meet per Week
Weeks of Program
Initial Training Hours
Amount of paid planning time per session (enter in hours)
Cost per Tutor of Background Checks/ Fingerprinting
Cost per Tutor for other related needs (ie benefits)
Other tutor related costs - Recruitment (flat amount)
|  |  | Estimated Hourly Tutors Needed |  | #DIV/0!
|  |  | Estimated Tutor Cost (overall) - Hourly |  |  | 0
|  |  | Estimated Tutor Cost (overall) - Salary |  |  | 0
Materials
Suggested 6% Analyzing expenditures of multiple tutoring programs, the average percent of total funds spent was approximately 6%. Materials likely will flucuate between 5-10% of the overall budget depending on what the district already has available. For example, if using a curriculum provided by TEA, may be $0. | 6% | 0 | Curriculum (digital and print) (flat amount)
Curriculum (digital and print) (price per student)
Assessment (flat amount)
Assessment (price per student)
Tech: Student + Tutor (i.e. headphones, laptops) (flat amount)
Tech: Student (i.e. headphones, laptops) (price per student)
Tech: Tutor (i.e. headphones, laptops) (price per tutor)
Platforms (attendance, scheduling) (flat amount)
Other (i.e. manipulatives) (flat amount)
|  |  | Estimated Materials Cost |  | #DIV/0! | #DIV/0!
Support Personnel |  |  |  | Time Allotment
Suggested 9% Analyzing expenditures of multiple tutoring programs, the average percent of total funds spent was approximately 9%. It would not be out of the ordinary for this to range from 5% - 15%. Questions to consider: Even if the district has these roles already (for ex: a data coordinator), is that role as is able to take on the added load related to tutoring or will additional hires be needed? | 9% | 0 | Senior Project Sponsor | 0.25
|  |  | Tutoring Program Lead | 2
School Site Manager(s)
|  |  | Tutor Coach(es) | 1.5
Curriculum & Instruction Lead
Technology Lead
Data Lead
Diverse Learner Lead
Teacher Advisory Group
|  |  | Estimated Personnel Cost |  | 0 | 0
Other
Overhead / Additional Operation Costs Suggested 10% Remaining budget may need to go to things like student transporation if outside of regular school hours, food for events, personnel travel, etc. | 10% | 0 | Overhead (flat amount) |  | 0
Reserves Suggested 5% Because the unexpected can happen (i.e.a few more students participate than initially planned for, each tutor can't take the exact number of groups in the model, etc), it is suggested to have reserved money to cover any unplanned costs so not to have to decrease other amounts already spoken for | 5% | 0 | Contingency Reserve |  | 0
|  |  | Estimate Other Costs |  | 0 | 0

## Implementation Project Plan
NOTE: This is still a work in progress; once feedback is received on all four outlines this will be finalized
Bucket | Task | Description | Person Responsible | Related Support People | Deadline | Status | Notes
Choosing HQIM | Assemble review team
Choosing HQIM | Create Rubric
Choosing HQIM | Host Review
Choosing HQIM | Discuss costs with vendors
Choosing HQIM | Identify HQIM
Choosing HQIM | Purchase HQIM
Identifying Students | Create guidance for selection
Identifying Students | School buy-in
Identifying Students | Determine when placement assessments will be given
School Communication | Share expectations regarding participating
School Communication | Plan kick off meeting
School Communication | Plan ongoing communication cycle
School Communication | Plan data review check points and follow up

## RACI Matrix
I = Informed & kept in the loop on the progress, rather than roped into details
R = Responsible, does work to complete tasks A = Accountable, delegates work, last one to review deliverable before deeming it complete C = Consulted, and provide input based on how it will impact future work I = Informed & kept in the loop on the progress, rather than roped into details |  | Senior Project Sponsor (Superintendent or Chief Academic Officer recommended) | Tutoring Program Lead (Instructional expertise recommended) | School Site Manager (Member of school leadership team) | Tutor Coaches (Can be at the district or campus level) | Curriculum & Instruction Lead | Technology Lead | Data Lead | Human Resource Representative | Diverse Learner Lead (Special education or MTSS lead recommended) | Teacher Advisory Group | Tutors
Strategy + Direction | Ensure tutoring initiative is sufficiently resourced and prioritized across the LEA
Set vision and strategy for tutoring initiative
Steers team toward project outcomes, works to remove barriers to team progress
Serves as primary point of contact for tutoring provider
Consistently brings diverse learner lens to proposed plans, tools, and training to advance access for all students
Project manages the program internally
Regularly convenes district leadership to share updates on progress
Ensures strong implementation of tutoring program at the campus
Human Resources | Develops a performance measurement plan for the program
Actively partners with tutoring team to recruit tutors
Actively partners with tutoring team to hire tutors
Determines substitute tutor plan
Manages substitute tutor plan
Licensing Products | Ensures all tutors have access to high quality instructional materials
Enrolls all students and tutors in applicable products
Training and Support | Assists with tutor training around instructional materials
Provides school based training
Coordinates with school site managers to align materials to classroom instruction
Actively partners with tutoring team to initially train tutors
Oversees tutor ongoing training and answers ongoing questions from tutors
Provides feedback on strategies to facilitate adjustments when needed
Scheduling and Operations | Coordinates across teams to ensure site managers have a plan for scheduling, food, transportation, etc.
Coordinates with site managers to troubleshoot any arising technology access issues
Ensures all students are equipped with necessary devices, programs, and connectivity to engage in tutoring sessions
Creates student schedules inclusive of tutoring
Creates master schedule inclusive of tutoring
Assessments | Ensures benchmark and progress monitoring systems are in place
Administers benchmark assessments
Administers progress monitoring assessments
Intervention Groups | Ensures strong implementation of tutoring program among diverse learners, including English learners and students with learning disabilities
Collects participating student information from schools
Creates groups
Matches tutors to groups
Communication | Manages student and parent communication
Facilitates tutor communication
Provides feedback from tutors to central team + school
Manages tutor and teacher communication
Manages LEA and school communication
Evalutation | Reviews tutoring session data and coordinates with tutors as needed to ensure alignment of key content with tutoring sessions
Supports tutoring provider and Program Lead in data reporting
Analyzes benchmark and progress monitoring data
Monitors attendance